## Sheet1
Project Name | Aardvark |  | Date |  | 2023-02-04 | Project Manager |  | Dallan Adamson
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Aardvark is a web application that is designed to be used by companies as an internal type of stack overflow. Users will be able to post their error messages and solutions to problems and then future employees experiencing the same issues will be able to look up those same problems and solutions. |  |  |  | Decide on Frameworks and technologies to use |  | 100% | Complete |  | 2023-01-30
|  |  |  | Draft the database |  | 100% | Complete |  | 2023-02-03
|  |  |  | Complete OrgChart |  | 100% | Complete |  | 2023-02-02
|  |  |  | Learn the front end framework |  | 50% | In progress
|  |  |  | Meet again week of Feb 6th to discuess further direction |  | 0% | Future Task
|  |  |  | Update Design and tweak docs |  | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
* Decided on technologies to use to develop the product * Completed OrgChart * Finish initial prototype | [5 empty] | * Development team learning front end framework * Meet week of 2/6 for planning and tweaking
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Dallan Adamson | Project Manager | 4 | Risk | Coding delays due to lack of front-end experience in the framework we chose to use
Colby Lyman | Front end developer | 4
Dallin Bowie | Project Designer/ developer | 3
Angle Wheelwright | Database engineer | 4 | Issue | Slow start to the project, still finalizing organization
Jared Wilson | Back end engineer | 5
Ren Strauss | Front end developer | 3
Jeremy Payne | Back end engineer | 3
Total